## Sheet1
Project/Release | Date | Project Status | Start Date | End Date | Total Stories | Completed Stories | Test Cases Designed | Story Tests Executed | Story Test Total | Open Defects | Defects Closed Today | Regression Test Executed | Regression Test Total
SLA/release may | 2025-07-22 | On Track | 2025-05-14 | 2025-05-27 | 4 | 1 | 5 | 2 | 5 | 8 | 0 | 0 | 0
GCP/release dec | 2025-07-22 | At Risk | 2025-05-01 | 2025-05-31 | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
APP 25.40/release feb | 2025-07-22 | Risk | 2025-03-03 | 2025-05-15 | 2 | 1 | 2 | 1 | 2 | 1 | 0 | 0 | 0
APP 25.45/release june | 2025-07-22 | On Track | 2025-06-03 | 2025-08-07 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rentch/release jan | 2025-07-22 | Risk | 2025-02-04 | 2025-04-17 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0

## Text_Summary_REPORT
Project/Release: SLA/release may (Status: On Track)
Start Date: 2025-05-14 ¦ End Date: 2025-05-27
5 Test cases designed (fixVersion).
Story Testing - 2 out of 5 test cases executed.
4 {'story' if total_stories == 1 else 'stories'} in scope + Regression.
* 8 defect(s) still open and 0 defect(s) closed today.
* Regression Testing - 0 out of 0 test cases executed.
Project/Release: GCP/release dec (Status: At Risk)
Start Date: 2025-05-01 ¦ End Date: 2025-05-31
1 Test case designed (fixVersion).
Story Testing - 1 out of 1 test case executed.
5 {'story' if total_stories == 1 else 'stories'} in scope + Regression.
* 1 defect(s) still open and 0 defect(s) closed today.
* Regression Testing - 0 out of 0 test cases executed.
Project/Release: APP 25.40/release feb (Status: Risk)
Start Date: 2025-03-03 ¦ End Date: 2025-05-15
2 Test cases designed (fixVersion).
Story Testing - 1 out of 2 test cases executed.
2 {'story' if total_stories == 1 else 'stories'} in scope + Regression.
* 1 defect(s) still open and 0 defect(s) closed today.
* Regression Testing - 0 out of 0 test cases executed.
Project/Release: APP 25.45/release june (Status: On Track)
Start Date: 2025-06-03 ¦ End Date: 2025-08-07
0 Test cases designed (fixVersion).
Story Testing - 0 out of 0 test cases executed.
2 {'story' if total_stories == 1 else 'stories'} in scope + Regression.
* 0 defect(s) still open and 0 defect(s) closed today.
* Regression Testing - 0 out of 0 test cases executed.
Project/Release: Rentch/release jan (Status: Risk)
Start Date: 2025-02-04 ¦ End Date: 2025-04-17
0 Test cases designed (fixVersion).
Story Testing - 0 out of 0 test cases executed.
1 {'story' if total_stories == 1 else 'stories'} in scope + Regression.
* 1 defect(s) still open and 0 defect(s) closed today.
* Regression Testing - 0 out of 0 test cases executed.